## Sheet1
项目进度计划project schedule | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6
阶段 phase | 任务 task | 摘要 summary | 开始日期start date | 结束日期 end date | 责任人/部门responsible person/department | 备注 remarks
前期准备阶段preparation stage | 合同签署 execution of contract | 包括双方合作商务合同，流程操作合同 including the bilateral business cooperation contract and the process operation contract | 2025-08-08 | 2025-08-11 | 裴先生、杨先生 | 关键启动条件 key start-up conditions
| 方案设计 proposal design | 这里的方案包括装修方案、采购方案、人员配置方案 The plans here include the renovation plan, procurement plan, and staffing plan. | 2025-08-10 | 2025-08-15 | 王先生、杨先生 | 与合同并行、增加胡志明出差In parallel with the contract, add a business trip to Ho Chi Minh City.
| 前期团队搭建initial team formation | 根据人员配置方案进行前期团队的人员招聘、入职工作、公司设立等 According to the staffing plan, carry out personnel recruitment for the initial team, onboarding, company establishment, and other related tasks. | 2025-08-15 | 2025-08-25 | 马先生、杨先生 | 核心成员到位即可进入实施Implementation can begin once the core members are in place.
| 预算审核 budget review | 预算审核包括装修预算、设施设备预算、零星货物预算、工资预算 The budget review includes the renovation budget, facilities and equipment budget, miscellaneous goods budget, and salary budget. | 2025-08-10 | 2025-08-20 | 王先生、龙先生 | 初期启动预算 initial start-up budget
| 资产租赁 asset leasing | 场地租赁 venue leasing | 2025-08-10 | 2025-08-15 | 裴先生、杨先生 | 与场地搭建衔接 coordinate with venue setup
实施阶段implementation stage | 场地搭建 venue setup | 进入装修期、按装修方案进行 Enter the renovation phase and proceed according to the renovation plan. | 2025-08-25 | 2025-09-30 | 裴先生、杨先生 | 不与其他项冲突 no conflict with other items
| 人员招聘 personnel recruitment | 根据人员配置进行人员招聘并完成入职、入职前培训 Recruit personnel according to the staffing plan, complete onboarding, and conduct pre-employment training. | 2025-08-05 | 2025-09-30 | 马先生、杨先生 | 培训前到岗 arrive before training
| 设计团队组织结构design team organizational structure | 根据人员招聘情况、确认公司组织结构并完成入职流程 Based on the recruitment status, confirm the company’s organizational structure and complete the onboarding process. | 2025-08-18 | 2025-08-25 | 王先生、马先生、杨先生 | 与人员招聘并行 in parallel with personnel recruitment
| 设备采购 equipment procurement | 确认购买地及采购、应符合越南公司法、避免出现账务漏洞并进行到场准备 Confirm the purchase location and procurement, ensure compliance with the Vietnam Company Law, avoid accounting loopholes, and carry out on-site preparations. | 2025-08-25 | 2025-09-10 | 王先生、杨先生 | 分批到货 delivered in batches
| 人员培训 personnel training | 业务培训 business training | 2025-09-10 | 2025-09-30 | 马先生、马先生助理 | 培训后可直接进入上线准备After training, can directly proceed to go-live preparation.
上线阶段 go-live phase | 设备调试 equipment debugging | 完成系统调试、测试、问题修复与最终交付Complete system debugging, testing, issue resolution, and final delivery. | 2025-09-20 | 2025-10-01 | 马先生、设备方 | 确保系统稳定 Ensure system stability
| 团队测试 team testing | 根据团队组织结构进行搭建、调整 Build and adjust according to the team’s organizational structure. | 2025-10-01 | 2025-10-07 | 马先生 | 覆盖所有业务流程 Cover all business processes
| 问题修复 problem fixing | 完成测试后、进行相应调整 Make corresponding adjustments after completing the testing. | 2025-10-03 | 2025-10-07 | 王先生、马先生、杨先生 | 快速响应问题单 quick response to issue tickets
| 零星问题处理 minor issue fixing | 最后调整并确认后续工作程序 Make final adjustments and confirm subsequent work procedures. | 2025-10-05 | 2025-10-15 | 马先生 | 最后验收与交付 final acceptance and delivery